## 工作表2
Division of tasks for organization of ACL 2016 Berlin between Local Organizer and ACL Business Office
DRAFT 2014-07-01
"X" indicates sole or joint perticipation in the task
TASKS | Local Organizer | ACL Business Office | Others
PRE-CONFERENCE PLANNING
Hotel site selection (with site visit) | X | X
Hotel contract negotiation/signing | X | X | ACL Treasurer actually signs
Selecting/site visiting of facilities for Welcoming Reception | X-primary | X-collaborate
Arranging for host to pay invoices(tax exempt) if possible | X
Providing funds to host institution to pay invoices |  | X
Banquet or Social Event site selection | X | X | with General Chair approval
Banquet site contract negotiations/signing | X | X | ACL Treasurer actually signs
Hiring Banquet buses and organizing trip | X | X -lesser extent
Creating budget and continually updating it; ultimately setting registration fees; etc. | X-collaborate | X consultation and adding non-local costs (pubs, awards, honoraria, etc.)-primarily | In consultation w/General Chair and ACL Treasurer as needed for final approval
Website development and continual updating | X
and adding links (to hotel, other chairs, MapQuest,Banquet,
ACL home page, etc), in consultation w/Prog, Spons, Exhib,
publicity, demo/poster chairs
Enlisting Volunteer Coordinator | X | X -lesser extent
Working with Volunteer Coordinator | X | X primarily
Send call for Volunteers | X -lesser extent | X | Volunteer Coordinator
Dormitory negotiation, reservation, registration | X |  | Univ or hosting inst. Staff
CLOSER TO CONFERENCE
Coordinate/track av requirements for each room w/chairs | X
and communicate needs to hotel; assure we have all we
need but stay within budget
Coordinate room layout with hotel | X-collaborate | X-advisory-collaborate
Develop online registration/payment form |  | X | ACL Treasurer & online developer
Test form/payment | X lesser extent | X | ACL Exec and others with different types of computers and software
Handle pre-conference registrations |  | X
Select catering menus at hotel | X-collarboate | X-collaborate
Select catering menus for Welcoming Reception | X
Select catering menus for Banquet | X
Order Bags, badge holders, gifts |  | X
Gather sponsor logos and send to suppliers | X |  | Sponsor chair
Create conference brochure | X
Gather handouts from Bureau of Conventions & Tourism | X | X-provide leads/ideas
Gather/receive shipments for bag stuffing, exhibitor and | X | X-as needed
publisher display items, proceedings, etc.
Arrange for any extra meetings (space and food) | X | X -collaborate
Coordinate exact volunteers/schedule w/Coordinator |  | X
Prepare Daily room-by-room schedules and other signs | X
Make sure exhibitors have what they need | X |  | Exhibits chair
Make sure demo/poster session poster boards, etc are ordered | X | X-consultation or done
On-Site
Bag and badge stuffing day before all begins | X | X-primary
Registrations |  | X
Coordinate/work with volunteers |  | X
Creating Participants List | X-getting copies | X-producing list
Ensure rooms and av are set and functioning at all times | X
Change room program schedules posted at doors each day | X
Arrange/set up poster/demo session space w/hotel people | X | X-consultation
Trouble-shooting at hotel | X | X-primary | General Chair
Trouble-shooting at any off-site locations | X
Post-Conference
Updating/finalizing registration database |  | X
Reviewing/approving final hotel bill (catering, av, space, etc) | X-lesser extent | X-consultation-primary
Reviewing/approving final banquet bill | X-lesser extent | X-consultation-primary
Reviewing/approving final host institution bill | X
Paying final bills | X-through host inst. | X-non local payments and to host
Updating/finalizing budget | X-lesser extent | X-non local payments-primary | General Chair-oversight